## Project Order
Task Group | Order | Dependency | BPM Application | Technologies used | Resource | AR # | Hours remaining to Complete AR
AWD Integrations | 1 |  | AWD Data Propagation | Java | Patel/Thompson | 141717 | 240
AWD Integrations | 2 | 141717 | AWD OK-Exit Button | Java/VB | Patel/Thompson | 141718 | 240
AWD Integrations | 3 | 141717 | AWD Auto Re-Index | Java | Patel | 141719 | 235.2
AWD Integrations | 4 | 141717 | AWD FileNet Viewer Service | Java/VB | Patel/Thompson | 141720 | 46
AWD Integrations | 5 |  | AWD More Button | Java/VB | Nannuri | 141721 | 147.2
AWD Integrations | 6 |  | AWD ROS | Java/VB | Pandey/Thompson | 141725 | 187
AWD Integrations | 7 |  | AWD TIFF-Split | Java/VB | Nannuri | 141726 | 184
AWD Integrations | 8 |  | AWD Select Person Button | Java/VB | Nannuri/Thompson | 141722 | 400
AWD Integrations | 9 |  | FNISSecurity Web-service | Java/VB/C# | Tripathi/Thompson/Pandey | 141709 | 299
AWD Integrations | 10 |  | AWD Doc Copy | Java | Nannuri | 141724 | 267
AWD Integrations | 11 |  | AWD Work Item Cloner + | Java | Pandey | 141727 | 296
AWD Integrations | 12 |  | AWD VB Mega | Java | Nannuri | 141723 | 337
AWD Integrations | 13 |  | AWD Policy Assembly | Java | Pandey | 141714 | 259
AWD Integrations | 14 |  | CPL Print Facility | ASP/VB | Patel | 141704 | 18
AWD Integrations | 15 |  | BPM WS | Java | Nannuri | 141710 | 230
BPM Integrations | 16 |  | Mainframe Parser | Java | Patel | 141715 | 267
BPM Integrations | 17 |  | CRDS Search | Java | Pandey | 141716 | 328
BPM Integrations | 18 |  | DataImEx | C# | Tripathi | 140784 | 689
BPM Integrations | 19 |  | LegalHold | C# | Tripathi | 141708 | 378
BPM Integrations | 20 | 140785 | Docustream Extract | C# | Tripathi | 141706 | 209
BPM Integrations | 21 | 141706 | Docusync | Java | Patel | 141712 | 294
BPM Integrations | 22 |  | NB Sharp Extract | C# | Adelphia |  | 150
BPM Integrations | 23 |  | InputAccel - P8 Export Module | C# | Harvey | 140725 | 207
BPM Integrations | 24 |  | InputAccel Group C | VBA/C# | Kandukuri | 140725 | 265
BPM Integrations | 25 | 140725 | InputAccel Group E | VBA/C# | Kandukuri | 140785 | 310
BPM Integrations | 26 | 140785 | Reconciliation Reporting Web Apps (Rightfax and Document Upload Facility) | C# | Adelphia | 141713 | 69